## Sheet1
PERMITS AND APPROVALS
Description | Institution | Observations | File | Date Started | Date Finish
Imminent Domain Report | National Emergency Commission |  | DPM-INF-1699/2007 |  | 22/10/2007
Imminent Domain Study of High Tension Power Lines | ICE | Property is not affected by any transmissions lines | 2110-617-2008 | 2008-06-05 | 16/05/2008
River Alignment | INVU |  | 20234 |  | 2007-10-10
Road Alignment, indicates that the property is not affected by any MOPT road project | MOPT | Property is not Affected by any Road Project | DPV-OF-7532-07 | 2007-02-10 | 2007-10-10
Use of the land | Municipality | Certified and Approved in accordance with use of the land | US 420-07 | 2007-04-10 | 2007-08-10
Rain Drainage | Municipality | Municipal Letter Approving Rain Drainage | US 421-07 | 2007-04-10 | 2007-08-10
Solid waste | Municipality | Letter of approval Concerning solid waste collection | OIM 098-08 | 2008-07-04 | 25/04/2008
Road Alignment and Construction Line | Municipality | Approved for Construction Line | OIM 097-08 | 2007-04-10 | 25/04/2008
Protected Areas | MINAE | Property has no protected Areas or Wetlands | ACOPAC-OSRAP-00282-08 | 14/03/2008 | 2008-02-04
Permit for Location of Sewage Treatment Plant | Health Ministry | Approved Permit for location of Sewage treatment Plant | UPAHP-12-08 |  | 21/05/2008
Environmental Impact study | SETENA | Approved |  | 2008-03-04
Preliminaries Studies Pending
Description | Institution | Observations | File | Date Started | Date Finish
Availability of Drinking Water | ASADA | Property had 80 water hookup available at the time of study | S.N.O. |  | 21/04/2008
Participation in the improvement of the Aqueduct in Esterillos Oeste | ASADA | Contract for additional municipal water hookups approved and Installation to begin within 30 days. New availability study forthcoming upon completition
Telephone and Electricity | ICE | In process
Master Site Plan Approval | I.N.V.U | In process |  | 21/04/2008